# Client Project Proposal & Sprint 1 Plan

TEMPLATE & INSTRUCTIONS

## Project Details

Project name: Client & Partner Relationship Management (CRM)

Client / organization: Food Systems Collective (FSC)

Prepared by: Client and PRM / team B: 46

Date of client discussion: 14/08/2026

## Team & Roles

| Role | Assigned to | Notes |
| --- | --- | --- |
| PM | David Zytsel | Project coordination, client communication, sprint planning |
| BA | Piotr Wesolowski | Requirement analysis, stakeholder/data modelling and requirements clarification |
| UX | Tommy Ngo | User flows, wireframes, UX design and prototype |
| DEV | Saneli Thathsari Ratnayake | Infrastructure and application development |
| DEV | Jason Xu | Infrastructure and application development |

## Problem Statement

The Food Systems Collective currently uses a CRM system that runs on Google sheets for tracking stakeholders and stakeholder engagement activities. With the expansion of the organisation, the current CRM system is now proving to be problematic due to factors such as poor record entry, duplication of entries, lack of visibility of stakeholder connections and history of interaction, among others. The project seeks to develop a more organised and effective CRM system.

## Target Users

The main users would be the Food Systems Collective team members who are tasked with managing stakeholder data and stakeholder interaction.

## Proposed Solution

A CRM system which would allow the FSC employees to manage their stakeholders in a centralised system. The solution would cover such areas as stakeholder profiles, relationships management, interaction tracking, scheduling of meetings, search and filers, and access rights, among others, depending on customer requirements and technical feasibility.

## Scope Boundaries

Core stakeholder management functions, which consist of stakeholder profiles, tagging and status, relationship management, meeting management. Any additional functions that can be realistically accomplished within time and technical constraints will be added as secondary functions.

Internship Management (Epic7). This was confirmed with the client. Meeting transcription and third party calendar integration are not part of the project at this point because of technical difficulties, as well as an official restriction on third party integrations.

## 3-Sprint Roadmap

Sprint 1 — Design & Bootstrap:

By the end of Sprint 1, the project infrastructure will be live and the team will have a confirmed MVP scope, requirements, system architecture, and validated UX prototype.

Sprint 2 — Raw MVP:

By the end of sprint 2, FSC users will be able to complete the core stakeholder management workflow from creating and viewing a stakeholder through to updating, organising, and searching stakeholder records.

Sprint 3 — Refine MVP:

By the end of sprint 3, the core stakeholder management MVP will be tested, refined, and polished. With additional priority features implemented where time and technical feasibility allow.

## Success Criteria

By the end of the project, FSC will have an operational CRM MVP through which the management of stakeholder’s information and relationships can be efficiently done in a systematic manner. The users will have the ability to log into system, maintain records of the stakeholders, search for information, and document interactions, all tested for the client.

The MVP should allow authorised users to:

- Log into the system

- Create and maintain stakeholder records

- View and update stakeholder information

- Organise and filter stakeholder records

- Record stakeholder records

- Manage relevant meeting information

- Access functionality according to their assigned permissions

## Assumptions & Constraints

Assumptions:

- The client will provide access to their existing Google Sheets CRM. Rose confirmed on 8th of August that she would send these via email/GitHub. Our understanding of the data model and the accuracy of the proposal will depend on receiving them early in the first sprint.

- The client stated that they revise and reissue the requirements presentation. This proposal is based on the version that was presented on 8th of August and will need to be reconciled if there are any updates.

- The features list still has not yet been formally prioritised by the client. Client has agreed to send a ranked list of must have feature and “nice to have” features.

Constraints:

- The clients' requirements/” nice to haves” imply that we will need APIs for meeting and calendar integrations, but it has been stated in the presentation that there are limitations with third party software integrations. Therefore, will need to propose manual file attachments instead.

- Epic 7 was out of scope, confirmed by the client on 8th of August, including any intern-related reporting from Epic 10.

- The scope volume was large, with 15 epics and over 60 individual features, this will largely exceed what is deliverable in the available time, sprint 2 will target the core features for the CRM.

## Client Agreement

Client name: [Name]

Client signature / date: [Signature / Date]

Team representative: David Zytsel

Team signature / date: David Zytsel, Piotr Wesolowki, Tommy Ngo, Saneli Thathsari Ratnayake, Jason Xu 04/08/2026

# Part B — Sprint 1 Plan (Weeks 1–3)

## Week 1

### Task 1: Review existing CRM and requirements

| Owner | Piotr Wesolowski / BA | Track | Design / Product |
| --- | --- | --- | --- |
| Week | 1 | Hours | 4 |

Description: Review the clients existing google sheets CRM and available requirements documentation to identify current stakeholder data fields, workflows, terminology, duplicate data, and existing processes

Deliverable: Initial requirements and CRM analysis document.

Acceptance criteria:

- Existing CRM structure reviewed

- Key stakeholder fields identified

- Existing workflow documented

- Major data/process problems documented

### Task 2: Confirm project scope and priorities

| Owner | David Zytsel / PM | Track | Design / Product |
| --- | --- | --- | --- |
| Week | 1 | Hours | 4 |

Description: Meet with FSC to confirm the priority of proposed features and resolve outstanding scope questions.

Deliverable:  Agreed scope and requirements decision log.

Acceptance criteria:

- Tier 1 features reviewed with client

- Tier 2 features reviewed

- Delayed features identified

- Epic 3 discussed

- Industry partners requirements discussed

- Calendar integration requirement discussed

- Meeting transcription requirement discussed

- Outstanding decisions documented

### Task 3: Set up development repository and environments

| Owner | Saleni Thathsari Ratnayke / DEV | Track | Infrastructure |
| --- | --- | --- | --- |
| Week | 1 | Hours | 4 |

Description: Establish the development repository and required development environment for the project

Deliverable:  Working project repository and development environment

Acceptance criteria:

- Repository configured

- Development environment documented

- Team members can access project

- Basic project structure established

### Task 4: Initial server and database setup

| Owner | Jason Xu / Dev | Track | Infrastructure |
| --- | --- | --- | --- |
| Week | 1 | Hours | 4 |

Description: Provision the initial web server and database environment that will be used throughout the project.

Deliverable:  Accessible development server and database

Acceptance criteria:

- Server provisioned

- Database provisioned

- Connection confirmed

- Environment configuration documented

### Task 5: Initial UX research and user flows

| Owner | Tommy Ngo / UX | Track | Design / Product |
| --- | --- | --- | --- |
| Week | 1 | Hours | 4 |

Description: Based on the confirmed requirements and existing CRM, identify the main user journeys for the CRM MVP

Deliverable:  Initial user flows for core stakeholder management

Acceptance criteria:

- Primary users identified

- Stakeholder management journey mapped

- Search/filter journey mapped

- Interaction/meeting journey mapped

- Initial navigation structure proposed

## Week 2

### Task 6: Define CRM data model

| Owner | Piotr Wesolowski / BA | Track | Design / Product |
| --- | --- | --- | --- |
| Week | 2 | Hours | 4 |

Description: Translate the existing CRM and confirmed requirements into a proposed data model covering stakeholders, tags, statuses, relationships, interactions, meetings, and users.

Deliverable: Approved/proposed CRM data model

Acceptance criteria:

- Stakeholder fields defined

- Tags/statuses defined

- Interaction structure defined

- Meeting structure defined

- User/permission requirements documented

- Outstanding data questions identified

### Task 7: Database architecture

| Owner | Saneli Thathari Ratnayake / DEV | Track | Infrastructure |
| --- | --- | --- | --- |
| Week | 2 | Hours | 4 |

Description: Translate the agreed data requirements into the technical database architecture without implementing working CRM features.

Deliverable: Database schema/design

Acceptance criteria:

- Tables/entities identified

- Relationships defined

- Required fields documented

- Schema reviewed against BA requirements

### Task 8: Define CRM data model

| Owner | Jason Xu / DEV | Track | Infrastructure |
| --- | --- | --- | --- |
| Week | 2 | Hours | 4 |

Description: Define the technical architecture for application hosting, database access, authentication, and potential file attachments.

Deliverable: Technical architecture documentation

Acceptance criteria:

- Application architecture documented

- Database architecture documented

- Authentication approach documented

- File storage approach documented

- Deployment approach documented

### Task 9: Wireframes

| Owner | Tommy Ngo / UX | Track | Design / Product |
| --- | --- | --- | --- |
| Week | 2 | Hours | 4 |

Description: Create wireframes for the primary CRM screens based on the confirmed requirements and user flows.

Deliverable: Initial CRM wireframes

Acceptance criteria:

- Stakeholder list designed

- Stakeholder profile designed

- Interaction/meeting interface designed

- Navigation structure represented

## Week 3

### Task 10: High fidelity CRM prototype

| Owner | Tommy Ngo / UX | Track | Design / Product |
| --- | --- | --- | --- |
| Week | 3 | Hours | 4 |

Description: Convert the approved wireframes into clickable prototype representing the core stakeholder management workflow.

Deliverable: Clickable prototype

Acceptance criteria:

- Main navigation represented

- Stakeholder creation flow represented

- Stakeholder viewing/editing represented

- Tags/statuses represented

- Prototype demonstrates the intended sprint 2 workflow

### Task 11: Infrastructure validation and deployment

| Owner | Jason Xu / DEV | Track | Infrastructure |
| --- | --- | --- | --- |
| Week | 3 | Hours | 4 |

Description: Validate the infrastructure established during sprint 1 and confirm that the development environment is accessible and ready for sprint 2 development.

Deliverable: Live and validated deployment environment.

Acceptance criteria:

- Server accessible

- Database accessible

- Application environment configured

- Storage approach validated

- Deployment approach validated

- Deployment process documented

### Task 12: Sprint 2 technical preparation

| Owner | Saneli Thathsari Ratnayake / DEV | Track | Infrastructure |
| --- | --- | --- | --- |
| Week | 3 | Hours | 4 |

Description: Review the sprint 2 technical requirements and ensure the infrastructure and architecture are ready for implementation of the core stakeholder management workflow.

Deliverable: Sprint 2 technical readiness checklist

Acceptance criteria:

- Sprint 2 core workflow reviewed

- Required technical dependencies identified

- Database design ready for implementation

- Development environment ready

- Technical risks documented

### Task 12: Final requirements and prototype review

| Owner | David Zytsel / PM | Track | Design / Product |
| --- | --- | --- | --- |
| Week | 3 | Hours | 4 |

Description: Conduct a final sprint 1 review with the team and client to confirm that the requirements, scope, and prototype are sufficiently clear for sprint 2 implementation

Deliverable: Sprint 1 sign off and sprint 2 scope

Acceptance criteria:

- Prototype reviewed

- Sprint 2 core feature confirmed

- Outstanding requirements documented

- Scope changes recorded

- Client feedback incorporated

- Sprint 2 priorities agreed